ParkPilot Smart Parking Platform

CIS 4374 - Semester Project

WE ARE $oftware ¢orp.

Fall 2026

Updated through Homework 6 - 10/12/2026

# 1. Existing Software Research

| Platform | What It Does | Limitation | How Our Platform Will Be Different |
| --- | --- | --- | --- |
| SpotHero | Search, compare, reserve, and prepay for parking. | Mainly focused on the driver reservation experience. | Add real-time occupancy tools and stronger parking-operator reporting. |
| PayByPhone | Digital parking payments, parking sessions, reminders, and selected reservation features. | Features vary by location and operator. | Provide one consistent system for availability, reservations, payments, and operator management. |
| ParkMobile | Parking reservations, event parking, destination search, and digital parking access. | Depends on participating locations and partnerships. | Combine driver features with real-time garage occupancy and operator analytics. |

Overall, the ParkPilot Smart Parking Platform will be different by combining the driver’s experience and parking-operator experience in one system. Drivers will be able to find, reserve, navigate to, and pay for parking, while operators can monitor occupancy and review reports and analytics.

# 2. Vision and Scope

## 2.1 How the Project Was Acquired

WE ARE $oftware ¢orp. acquired the project through a fictional Request for Proposal (RFP) from a city transportation department that wanted a better way to manage parking and reduce the time drivers spend searching for available spaces.

## 2.2 Fictional Company Introduction

WE ARE $oftware ¢orp. is a fictitious software development studio responsible for planning and managing the ParkPilot Smart Parking Platform. For this semester project, the company has unlimited theoretical resources and budget.

## 2.3 Rough Project Overview

The ParkPilot Smart Parking Platform will be available through web and mobile applications. It will help drivers locate available parking, reserve spaces, pay digitally, receive navigation assistance, and view reservation information. Parking operators will be able to monitor occupancy and review parking reports and analytics.

# 3. Draft Software Requirements Specification

## 3.1 Functional Requirements

FR-01: The system shall allow users to register and log in.

FR-02: The system shall display real-time parking availability.

FR-03: The system shall display parking locations on an interactive map.

FR-04: The system shall allow users to reserve parking.

FR-05: The system shall allow users to make digital payments.

FR-06: The system shall store reservation history and receipts.

FR-07: The system shall send parking-related notifications and alerts.

FR-08: The system shall provide navigation assistance through an external mapping service.

FR-09: The system shall provide parking operators with an administrative dashboard.

FR-10: The system shall generate occupancy reports and analytics.

FR-11: The system shall display the exact number of available parking spaces for each supported parking facility.

FR-12: The system shall allow users to filter parking results by EV charging availability and handicap-accessible parking.

FR-13: The system shall support dynamic parking prices based on demand and time.

FR-14: The system shall allow users to save favorite parking locations and submit ratings and reviews.

FR-15: The system shall support license plate recognition for vehicle identification and parking access.

FR-16: The system shall recommend parking garages to users based on factors such as price and distance.

FR-17: The system shall allow authorized parking operators to add, edit, and remove parking garages.

FR-18: The system shall allow authorized parking operators to manage parking pricing.

FR-19: The system shall generate operator reports for revenue, occupancy, busiest times, reservations, payment transactions, and garage performance.

FR-20: The system shall allow authorized parking operators to export financial reports.

## 3.2 Non-Functional Requirements

NFR-01: The system shall support at least 1,000 concurrent users.

NFR-02: The system shall update parking availability within 1 second after new occupancy data is received.

NFR-03: The system shall provide 99.99% uptime, excluding scheduled maintenance.

NFR-04: The parking search and availability screen shall load within 2 seconds for up to 1,000 concurrent users.

## 3.3 Use Cases

The following use cases represent the current ParkPilot system functionality and have been refined as the project requirements developed.

| ID | Use Case | Actor | Precondition | Steps | Postcondition |
| --- | --- | --- | --- | --- | --- |
| UC-01 | Register Account | Driver | App is available. | 1. Select register. 2. Enter information. 3. Submit. | Account is created. |
| UC-02 | Log In | Registered User | User has an account. | 1. Enter credentials. 2. System validates. 3. Continue. | User is logged in. |
| UC-03 | Manage Vehicle | Driver | User is logged in. | 1. Open vehicles. 2. Add/edit details. 3. Save. | Vehicle information is stored. |
| UC-04 | Search for Parking | Driver | App is available. | 1. Enter destination. 2. System searches. 3. View results. | Parking options are displayed. |
| UC-05 | View Availability | Driver | Parking area is selected. | 1. System retrieves data. 2. Display availability. | Current availability is shown. |
| UC-06 | View Facility Details | Driver | Facility is selected. | 1. Open facility. 2. View location, price, and availability. | Facility details are displayed. |
| UC-07 | Reserve Parking | Driver | User is logged in and parking is available. | 1. Choose date/time. 2. Review details. 3. Confirm. | Reservation is created. |
| UC-08 | Make Payment | Driver | A reservation requires payment. | 1. Choose payment. 2. Process payment. 3. Confirm. | Payment is recorded. |
| UC-09 | View Reservation | Driver | User has a reservation. | 1. Open reservations. 2. Select reservation. | Reservation details are displayed. |
| UC-10 | Cancel Reservation | Driver | Reservation is eligible for cancellation. | 1. Open reservation. 2. Select cancel. 3. Confirm. | Reservation is canceled. |
| UC-11 | View History/Receipt | Driver | User has past activity. | 1. Open history. 2. Select reservation. 3. View receipt. | Past reservation and receipt are shown. |
| UC-12 | Navigate to Facility | Driver | Facility is selected. | 1. Select navigate. 2. Send location to map service. | Directions are displayed. |
| UC-13 | Receive Notification | Driver | Notifications are enabled. | 1. System detects event. 2. Send alert. | Driver receives the alert. |
| UC-14 | Monitor Occupancy | Parking Operator | Operator is authorized. | 1. Open dashboard. 2. Retrieve occupancy. 3. Review status. | Current occupancy is displayed. |
| UC-15 | View Reports/Analytics | Parking Operator | Operator is authorized. | 1. Open reports. 2. Select period. 3. Generate report. | Occupancy and utilization report is displayed. |
| UC-16 | Filter Parking | Driver | Parking results are available. | 1. Open filters. 2. Select EV or accessible options. 3. Apply filters. | Matching parking options are displayed. |
| UC-17 | View Exact Open Spaces | Driver | Facility availability data is available. | 1. Select facility. 2. System retrieves occupancy count. 3. Display open spaces. | Exact open-space count is shown. |
| UC-18 | Save Favorite / Review | Driver | User is logged in. | 1. Select facility. 2. Save favorite or submit rating/review. 3. Confirm. | Favorite or review is stored. |
| UC-19 | Receive AI Garage Recommendation | Driver | Parking options are available. | 1. Enter destination. 2. System compares price and distance. 3. Display recommendation. | Recommended garage is shown. |
| UC-20 | Use License Plate Recognition | Driver | Vehicle plate is registered. | 1. Vehicle approaches supported access point. 2. System reads plate. 3. Validate vehicle/reservation. | Vehicle is identified for parking access. |
| UC-21 | Manage Garage | Parking Operator | Operator is authorized. | 1. Open garage management. 2. Add/edit/remove garage. 3. Save changes. | Garage information is updated. |
| UC-22 | Manage Pricing | Parking Operator | Operator is authorized. | 1. Open pricing. 2. Set base/dynamic pricing rules. 3. Save. | Parking pricing is updated. |
| UC-23 | View Revenue / Performance Reports | Parking Operator | Operator is authorized. | 1. Open reports. 2. Select report and period. 3. Generate. | Revenue/performance report is displayed. |
| UC-24 | Export Financial Report | Parking Operator | Financial report is available. | 1. Open financial report. 2. Select export. 3. Download file. | Financial report is exported. |
| UC-25 | Navigate to Reserved Space | Driver | User has an active reservation. | 1. Open reservation. 2. Select navigation. 3. Follow garage/space directions. | Driver is guided to the reserved space. |

3.4 User Stories

The user stories below align the current ParkPilot requirements with the needs of drivers and parking operators.

| ID | As a... | I want to... | So that... |
| --- | --- | --- | --- |
| US-01 | Driver | register and log in | I can securely access my ParkPilot account. |
| US-02 | Driver | see live parking availability and exact open-space counts | I can quickly find a garage with available parking. |
| US-03 | Driver | filter parking by EV charging and handicap accessibility | I can find parking that meets my needs. |
| US-04 | Driver | reserve and cancel a parking space | I can plan parking before arriving. |
| US-05 | Driver | pay digitally and receive a receipt | I can complete my parking transaction in the app. |
| US-06 | Driver | receive navigation to my garage and reserved space | I can reach my parking location easily. |
| US-07 | Driver | receive a garage recommendation based on price and distance | I can choose a convenient and cost-effective option. |
| US-08 | Driver | save favorites and submit ratings and reviews | I can reuse preferred garages and share feedback. |
| US-09 | Parking Operator | manage garages and parking prices | I can keep facility information and pricing current. |
| US-10 | Parking Operator | monitor occupancy and open-space counts | I can understand garage utilization in real time. |
| US-11 | Parking Operator | view revenue, occupancy, reservation, and performance reports | I can evaluate parking operations. |
| US-12 | Parking Operator | export financial reports | I can use ParkPilot data for financial review and reporting. |

Sources: SpotHero (spothero.com); PayByPhone (paybyphone.com); ParkMobile (parkmobile.io).

# 4. Work Breakdown Structure (WBS)

The WBS below breaks ParkPilot into three levels: major system areas, modules, and feature deliverables.

1. Driver Application

1.1 Authentication

•  Registration

•  Login / Logout

•  Password Recovery

1.2 Parking Search & Live Availability

•  Live map with green/red garage availability

•  Exact number of open spots

•  Search by destination

•  EV charging and handicap-accessible filters

1.3 Reservations & Navigation

•  Reserve a spot within a garage

•  Cancel reservation

•  Navigation to garage and reserved space

1.4 Payments & Driver Features

•  Credit/debit card, Apple Pay, Google Pay, and PayPal

•  Digital receipts

•  Favorites, ratings, and reviews

•  Parking notifications and alerts

2. Parking Operator Platform

2.1 Garage Management

•  Add, edit, and remove garages

•  Monitor occupancy and open-space count

2.2 Pricing Management

•  Base pricing

•  Dynamic pricing based on demand and time

2.3 Reporting & Analytics

•  Revenue and occupancy reports

•  Busiest-time analytics

•  Export financial reports

3. Backend & Integrations

3.1 Core Data Services

•  User, garage, reservation, and payment data

3.2 External Integrations

•  Mapping and indoor navigation services

•  Payment providers

•  License plate recognition

3.3 AI Recommendation System

•  Compare garage price and distance

•  Recommend the best garage to the driver

4. Quality Assurance & Testing

4.1 Driver Application Testing

•  Search, reservation, payment, and navigation testing

4.2 Operator Platform Testing

•  Dashboard, pricing, and reporting testing

4.3 Integration Testing

•  Mapping, payment, AI, and license plate recognition testing

# 5. Draft Timeline and Gantt Chart

The draft schedule below turns the WBS into a 10-week development timeline. Several work streams overlap because ParkPilot uses separate development teams for mobile, web, backend, mapping, payments, and testing.

| Week | Planned Work |
| --- | --- |
| Week 1 | Project setup, requirements review, and technical architecture |
| Week 2 | Authentication, core database, and garage/operator setup |
| Week 3 | Live parking map, occupancy feed, and exact open-space count |
| Week 4 | Search, EV/accessible filters, favorites, ratings, and reviews |
| Week 5 | Reservations and dynamic pricing |
| Week 6 | Card, Apple Pay, Google Pay, PayPal, and digital receipts |
| Week 7 | Garage navigation and license plate recognition |
| Week 8 | AI garage recommendation, notifications, and operator dashboard |
| Week 9 | Reporting, analytics, and full-system integration testing |
| Week 10 | Bug fixes, final testing, and release preparation |

## 5.1 Gantt Chart

| Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements & Architecture | X | X |  |  |  |  |  |  |  |  |
| Authentication & Core Database |  | X | X |  |  |  |  |  |  |  |
| Live Map & Availability |  |  | X | X |  |  |  |  |  |  |
| Search, Filters & Reviews |  |  |  | X | X |  |  |  |  |  |
| Reservations & Dynamic Pricing |  |  |  |  | X | X |  |  |  |  |
| Payments & Receipts |  |  |  |  |  | X | X |  |  |  |
| Navigation & License Plate Recognition |  |  |  |  |  |  | X | X |  |  |
| AI Recommendations & Notifications |  |  |  |  |  |  |  | X | X |  |
| Operator Dashboard, Reports & Analytics |  |  |  |  |  |  |  | X | X | X |
| Integration & System Testing |  |  |  |  |  |  |  |  | X | X |
| Final Review / Release Preparation |  |  |  |  |  |  |  |  |  | X |

# 6. Agile Project Management

The ParkPilot product backlog was organized in Jira using Scrum. The backlog contains 45 work items across login, user/operator interfaces, backend processes, and reporting. Eight foundational items were selected for Sprint 1.

## 6.1 Product Backlog

| Category | Backlog Item |
| --- | --- |
| Login | User Registration |
| Login | User Login |
| Login | User Logout |
| Login | Password Recovery |
| Login | Login Authentication and Validation |
| UI - User/Operator | User Parking Search Interface |
| UI - User/Operator | Live Parking Availability Map |
| UI - User/Operator | Garage Details Interface |
| UI - User/Operator | Parking Reservation Interface |
| UI - User/Operator | Payment Checkout Interface |
| UI - User/Operator | Reservation History and Receipts Interface |
| UI - User/Operator | Navigation Interface |
| UI - User/Operator | Favorites Interface |
| UI - User/Operator | Garage Ratings and Reviews Interface |
| UI - User/Operator | Parking Filters Interface |
| UI - User/Operator | Operator Dashboard Interface |
| UI - User/Operator | Operator Garage Management Interface |
| UI - User/Operator | Operator Pricing Management Interface |
| UI - User/Operator | Operator Occupancy Monitoring Interface |
| UI - User/Operator | Operator Reports and Analytics Interface |
| Backend - User/Operator | User Account Data Processing |
| Backend - User/Operator | Real-Time Parking Availability Processing |
| Backend - User/Operator | Parking Search Processing |
| Backend - User/Operator | Reservation Creation and Cancellation Processing |
| Backend - User/Operator | Dynamic Pricing Processing |
| Backend - User/Operator | Payment Processing |
| Backend - User/Operator | Receipt Generation |
| Backend - User/Operator | Navigation and Mapping Integration |
| Backend - User/Operator | License Plate Recognition Processing |
| Backend - User/Operator | Parking Notification Processing |
| Backend - User/Operator | AI Garage Recommendation Processing |
| Backend - User/Operator | Garage Management Processing |
| Backend - User/Operator | Occupancy Data Processing |
| Backend - User/Operator | Operator Pricing Update Processing |
| Backend - User/Operator | Favorites and Reviews Data Processing |
| Reporting - User/Operator | User Parking History Report |
| Reporting - User/Operator | User Payment and Receipt Report |
| Reporting - User/Operator | User Reservation History Report |
| Reporting - User/Operator | Operator Occupancy Report |
| Reporting - User/Operator | Operator Revenue Report |
| Reporting - User/Operator | Operator Busiest Times Report |
| Reporting - User/Operator | Operator Garage Performance Report |
| Reporting - User/Operator | Operator Reservation Activity Report |
| Reporting - User/Operator | Operator Payment Transaction Report |
| Reporting - User/Operator | Operator Financial Report Export |

## 6.2 Sprint 1 Backlog

Sprint 1 focuses on authentication/account functionality and the initial operator foundation. The sprint is active, with all eight committed work items currently in To Do and ready for development.

•  User Registration

•  User Login

•  User Logout

•  Password Recovery

•  Login Authentication and Validation

•  Operator Dashboard Interface

•  User Account Data Processing

•  Garage Management Processing

## 6.3 Jira Sprint 1 Board

The Jira screenshot below shows the active SCRUM Sprint 1 board. All eight committed work items are in To Do; no items are marked In Progress, In Review, or Done yet.

Figure 1. ParkPilot active SCRUM Sprint 1 board in Jira.

# 7. Risk and Communication Management

ParkPilot risks were identified across the four categories covered in Class 5: technical, schedule, financial, and people. A risk register was then created to assess and track key risks, followed by a communication plan for the project teams and stakeholders.

## 7.1 Identified Project Risks

| Category | ID | Risk Description |
| --- | --- | --- |
| Technical | T1 | Parking sensor or garage availability data may be inaccurate or delayed. |
| Technical | T2 | License plate recognition may incorrectly read a vehicle's plate. |
| Technical | T3 | Third-party services such as maps or payment processing may experience outages or integration failures. |
| Technical | T4 | Real-time parking availability may not update quickly enough during periods of high system traffic. |
| Schedule | S1 | Third-party API integrations may take longer than expected to implement and test. |
| Schedule | S2 | Development of complex features such as real-time availability, dynamic pricing, and license plate recognition may exceed their planned timelines. |
| Schedule | S3 | Bugs discovered during testing may require additional development time and delay later project tasks. |
| Schedule | S4 | Dependencies between frontend, backend, and database tasks may cause delays if one component is not completed on schedule. |
| Financial | F1 | Cloud hosting and database usage costs may exceed the planned budget as the number of users and transactions increases. |
| Financial | F2 | Third-party services such as mapping, payment processing, or license plate recognition may introduce higher-than-expected API or transaction fees. |
| Financial | F3 | Parking sensors, cameras, or other required hardware may cost more to purchase, install, or maintain than originally estimated. |
| Financial | F4 | Unexpected development or maintenance work may increase labor costs and push the project over budget. |
| People | P1 | A key team member may become unavailable or leave the project, causing loss of knowledge and delays. |
| People | P2 | Team members may lack experience with specialized technologies such as license plate recognition, real-time data processing, or payment integration. |
| People | P3 | Poor communication between frontend, backend, database, and testing team members may lead to misunderstandings or rework. |
| People | P4 | Uneven workload distribution may cause team members to become overloaded, reducing productivity and delaying assigned tasks. |

## 7.2 Risk Register

| ID | Risk Description | Probability | Impact | Owner | Response Strategy | Status / Notes |
| --- | --- | --- | --- | --- | --- | --- |
| T1 | Parking sensor or garage availability data may be inaccurate or delayed. | Moderate (3) | Major (4) | Backend Team | Mitigate | Monitor data accuracy and validate incoming occupancy data. |
| T2 | License plate recognition may incorrectly read a vehicle's plate. | Moderate (3) | Major (4) | Integration Team | Mitigate | Test recognition accuracy and provide a manual verification option. |
| T3 | Third-party mapping or payment services may experience outages or integration failures. | Moderate (3) | Major (4) | Integration Team | Mitigate | Monitor external services and design fallback/error-handling procedures. |
| S1 | Third-party API integrations may take longer than expected to implement and test. | Moderate (3) | Moderate (3) | Project Manager | Mitigate | Track integration progress and identify delays during progress meetings. |
| S2 | Complex features such as real-time availability, dynamic pricing, and license plate recognition may exceed planned timelines. | Moderate (3) | Major (4) | Project Manager | Mitigate | Break complex features into smaller tasks and monitor progress each sprint. |
| S3 | Bugs discovered during testing may require additional development time. | High (4) | Moderate (3) | QA Team | Mitigate | Test throughout development instead of waiting until the end. |
| F1 | Cloud hosting and database usage costs may exceed the planned budget as usage increases. | Moderate (3) | Moderate (3) | Project Manager | Mitigate | Monitor cloud usage and costs throughout development. |
| F3 | Parking sensors, cameras, or other required hardware may cost more to purchase, install, or maintain than estimated. | Moderate (3) | Major (4) | Project Manager | Mitigate | Review hardware costs early and compare available equipment options. |
| P1 | A key team member may become unavailable or leave the project. | Low (2) | Major (4) | Project Manager | Mitigate | Maintain documentation and cross-train team members on important project areas. |
| P3 | Poor communication between frontend, backend, database, and testing teams may cause misunderstandings or rework. | Moderate (3) | Major (4) | Project Manager | Mitigate | Use regular team meetings, Jira updates, and clearly assigned responsibilities. |

## 7.3 Communication Plan

| Team / Audience | Meeting Cadence | Purpose | Reporting Method |
| --- | --- | --- | --- |
| Project Team | Daily Stand-Up | Share current tasks, progress, and blockers | Jira board and verbal status updates |
| Development Team | Weekly Progress Meeting | Review frontend, backend, database, and integration progress | Jira task updates and GitHub activity |
| QA / Testing Team | Weekly Testing Review | Review defects, testing results, and unresolved issues | Test results and Jira issue tracking |
| Project Manager & Team Leads | Biweekly Progress Meeting | Review schedule, risks, milestones, and project status | Progress summary and Risk Register |
| Stakeholders / Client | Monthly Sprint Review | Demonstrate completed functionality and review overall progress | Product demo, dashboard, and progress report |

8. Resource and Cost Management

ParkPilot uses a seven-person cross-functional project team. A bottom-up estimate was used to calculate labor and non-labor costs for the 10-week project, followed by a three-month budgeted cash flow and a RACI matrix that assigns responsibility for major project activities.

8.1 Roles and Resources

| Role | Fictional Name | Skill Level | Allocation | Est. Hours | Main Responsibility |
| --- | --- | --- | --- | --- | --- |
| Project Manager | Alex Carter | Senior | 40% | 160 | Plans project, tracks schedule/costs, manages risks and communication |
| Developer 1 | Daniel Kim | Senior | 100% | 400 | Backend, database, availability, reservations, payments, and APIs |
| Developer 2 | Maya Patel | Intermediate | 100% | 400 | Driver/operator interfaces, live map, filters, and frontend |
| QA Tester | Jordan Lee | Intermediate | 50% | 200 | Creates test cases and tests features, integrations, and system behavior |
| UX Designer | Sofia Martinez | Intermediate | 30% | 120 | Designs driver/operator interfaces and improves usability |
| DevOps / Cloud Engineer | Ethan Brooks | Senior | 30% | 120 | Cloud infrastructure, deployment, monitoring, and reliability |
| Business Analyst / Product Owner | Olivia Chen | Senior | 30% | 120 | Manages requirements, prioritizes features, represents stakeholders |

8.2 Bottom-Up Resource and Cost Plan

| Role | Hours | Hourly Rate | Labor Cost |
| --- | --- | --- | --- |
| Project Manager | 160 | $60/hr | $9,600 |
| Developer 1 | 400 | $55/hr | $22,000 |
| Developer 2 | 400 | $45/hr | $18,000 |
| QA Tester | 200 | $35/hr | $7,000 |
| UX Designer | 120 | $40/hr | $4,800 |
| DevOps / Cloud Engineer | 120 | $55/hr | $6,600 |
| Business Analyst / Product Owner | 120 | $45/hr | $5,400 |
| TOTAL LABOR | 1,520 |  | $73,400 |
| Item | Category | Estimated Cost | Notes |
| Team Labor | Labor | $73,400 | 1,520 estimated project hours |
| Cloud Hosting & Database | Infrastructure | $2,000 | Hosting, database, storage, and monitoring |
| Maps & Navigation APIs | Third-Party API | $1,200 | Mapping and navigation functionality |
| Payment & LPR Services | Third-Party API | $1,500 | Payment integration and license plate recognition |
| Software & Development Tools | Licenses / Tools | $900 | Development, testing, and collaboration tools |
| Parking Sensors / Test Hardware | Hardware | $3,000 | Parking occupancy and testing hardware |
| Subtotal |  | $82,000 | Before contingency |
| Contingency | Reserve | $8,200 | 10% of subtotal |
| TOTAL ESTIMATED BUDGET |  | $90,200 |  |

8.3 Monthly Budgeted Cash Flow

| Cost Category | Month 1 | Month 2 | Month 3 | Total |
| --- | --- | --- | --- | --- |
| Labor | $29,360 | $29,360 | $14,680 | $73,400 |
| Cloud Hosting & Database | $700 | $700 | $600 | $2,000 |
| Maps & Navigation APIs | $300 | $400 | $500 | $1,200 |
| Payment & LPR Services | $200 | $500 | $800 | $1,500 |
| Software & Development Tools | $900 | $0 | $0 | $900 |
| Parking Sensors / Test Hardware | $3,000 | $0 | $0 | $3,000 |
| Contingency | $3,446 | $3,096 | $1,658 | $8,200 |
| MONTHLY TOTAL | $37,906 | $34,056 | $18,238 | $90,200 |

8.4 RACI Matrix

R = Responsible, A = Accountable, C = Consulted, I = Informed. PM = Project Manager, D1 = Developer 1, D2 = Developer 2, QA = QA Tester, UX = UX Designer, DO = DevOps / Cloud Engineer, BA/PO = Business Analyst / Product Owner.

| Project Activity | PM | D1 | D2 | QA | UX | DO | BA/PO |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements & Planning | A | C | C | I | C | I | R |
| System Architecture & Database | A | R | C | I | I | C | C |
| Driver & Operator UI | A | C | R | C | R | I | C |
| Live Parking & Occupancy | A | R | C | C | I | C | I |
| Reservations & Dynamic Pricing | A | R | C | C | I | I | C |
| Payments & External APIs | A | R | C | C | I | C | I |
| Navigation & License Plate Recognition | A | R | C | C | I | C | I |
| Testing & Quality Assurance | I | C | C | A/R | I | C | I |
| Cloud Deployment & Monitoring | C | C | I | C | I | A/R | I |
| Final Release & Project Approval | A | C | C | C | I | R | C |

# 9. References

Dobretsberger, Otto. Lecture 7: Tools & Technology. CIS 4374, University of Houston, Fall 2026.

Dobretsberger, Otto. Lecture 6: Resource & Cost Management. CIS 4374, University of Houston, Fall 2026.

Dobretsberger, Otto. Lecture 5: Risk, Quality, and Communication Management. CIS 4374, University of Houston, Fall 2026.

Dobretsberger, Otto. Lecture 4: Agile, Scrum, and Kanban. CIS 4374, University of Houston, Fall 2026.

Dobretsberger, Otto. Lecture 3: Estimation, Scheduling, and Work Breakdown. CIS 4374, University of Houston, Fall 2026.

Dobretsberger, Otto. Lecture 2: Kickoff, Requirements Gathering, and Documentation. CIS 4374, University of Houston, Fall 2026.

SpotHero. https://spothero.com/

PayByPhone. https://www.paybyphone.com/

ParkMobile. https://parkmobile.io/